## Slide 1
TECHCORP
IAM Platform Implementation Plan
A phased roadmap for secure, automated identity and access management across 100+ countries and 150,000+ employees
IAM Developer Solution Proposal - M Uzair | Implementation Phase

## Slide 2
1
Executive Overview
TechCorp's IAM readiness assessment and solution design are complete. This plan translates the approved design, automated user lifecycle management and role-based access control into a phased, resourced implementation that avoids disruption to daily operations.
Automate joiner / mover / leaver access across the employee lifecycle
Enforce least-privilege, role-based access with MFA and conditional access
Integrate legacy, third-party, and cloud applications via SSO and SCIM
Deliver centralized audit logging and continuous governance
150,000+
Employees Covered
100+
Countries
5
Rollout Phases
4
Core Standards
(SCIM · SAML · OIDC · OAuth2)
2

## Slide 3
2
Implementation Roadmap
1
Foundation
Weeks 1–4
Inventory identities, apps & privileged accounts; establish governance and identity data standards.
Milestone: Governance charter approved
2
Identity
Integration
Weeks 5–10
Connect HRIS to the identity platform; build Joiner-Mover-Leaver workflows.
Milestone: HRIS ↔ IdP live
3
Core Access
Weeks 11–18
Implement RBAC, groups, SSO and MFA; onboard highest-priority applications.
Milestone: Top-priority apps on SSO/MFA
4
Governance
Weeks 19–24
Introduce access reviews, segregation of duties, PAM and automated remediation.
Milestone: First access review cycle
5
Scale &
Optimise
Weeks 25–30+
Expand integrations globally, tune policies, automate reporting, continuous improvement.
Milestone: 80%+ apps integrated
3

## Slide 4
3
Delivery Timeline
Estimated duration by phase, in weeks from project kickoff
4

## Slide 5
4
Target Architecture & Integration Flow
HRIS
(Authoritative Source)
Identity Governance
& Lifecycle Engine
Central Identity
Provider (Entra ID)
SSO Applications
Cloud / SaaS
(SCIM Provisioning)
Privileged Access
(PAM)
Central Audit Logs + SIEM + Periodic Access Reviews
5

## Slide 6
5
Integration Challenges & Solutions
1
Legacy Systems
Challenge
No modern APIs or federation support; direct integration is impractical.
Our Approach
Route through a controlled gateway/connector layer; prioritise modernisation of the highest-risk legacy apps first.
2
Third-Party Applications
Challenge
Inconsistent support for SCIM, SAML or OIDC across vendors.
Our Approach
Use native standards where supported; fall back to secured API or brokered provisioning for the rest, with a migration path to standards-based access.
3
Cloud / SaaS Sprawl
Challenge
Rapid adoption of new SaaS creates uncontrolled identity sprawl and inconsistent access.
Our Approach
Federate every new cloud app through the central IdP via SSO and SCIM; onboard in priority order by risk and user count.
6

## Slide 7
6
Resource Requirements
1
Executive Sponsor & Steering Committee
Approves scope, budget and risk decisions; unblocks cross-functional dependencies.
2
IAM Program Manager
Owns the plan, timeline, milestones and stakeholder communication.
3
IAM Architects & Engineers
Configure the identity platform, RBAC model, SSO/SCIM connectors and PAM.
4
HRIS & Application Integration Leads
Deliver HRIS event feeds and application-side onboarding for SSO/SCIM.
5
Security / GRC Analyst
Defines access-review cadence, SoD rules and audit/compliance reporting.
6
Change Management & Training Lead
Prepares end users and application owners for MFA, SSO and new workflows.
Tooling: Microsoft Entra ID (reference IdP) · SCIM / SAML / OIDC / OAuth 2.0 connectors · SIEM integration · Access-review & PAM tooling
7

## Slide 8
7
Security & Access Controls
1
RBAC & Least Privilege
Roles map to business responsibilities; permissions follow the role, with approvals for sensitive resources.
2
MFA & Conditional Access
Mandatory MFA workforce-wide; phishing-resistant methods and device/risk signals for privileged and high-risk access.
3
Privileged Access Management
Just-in-time elevation, approval workflows, session logging and time-bound admin permissions.
4
Audit, SIEM & Access Reviews
All identity events centrally logged; periodic certification and segregation-of-duties checks.
8

## Slide 9
8
Alignment with Business Objectives
Security
Centralized auth, least privilege, MFA and PAM close common identity attack paths.
Efficiency
Automation removes manual provisioning, cuts errors, speeds up employee access.
User Experience
SSO reduces password fatigue with a consistent access experience everywhere.
Scalability
Role/group-based access and open standards support 150,000+ users across 100+ countries.
Competitive Edge
A secure, frictionless workplace lets TechCorp adopt new cloud services without identity sprawl.
9

## Slide 10
9
Success Metrics & Risk Mitigation
Success Metrics
% of joiners provisioned before start date
Time from termination event to disablement
% of apps on SSO / automated provisioning
% of users protected by MFA
Orphaned / dormant account count & age
% of access reviews completed on time
Key Risks & Mitigations
Poor HR data quality
Mandatory attributes, validation, clear ownership
Legacy apps lack standards
API/connector gateway; prioritise modernisation
Overly broad roles
Role mining, approvals, periodic access reviews
User resistance to MFA
SSO, communication, phishing-resistant methods
Global regulatory differences
Global baseline + country-specific overlays
10

## Slide 11
Conclusion
This phased plan gives TechCorp a scalable identity foundation: automated lifecycle management keeps access aligned with employment status, while RBAC, MFA, PAM and continuous monitoring protect critical resources. Starting with the highest-risk applications and expanding globally, IAM becomes part of how TechCorp works, not a separate security layer.
1
Confirm steering committee & kickoff date
2
Finalise HRIS integration scope for Phase 1
3
Approve budget and resourcing plan